## Cost Estimate
Project Cost Estimate
Project Name: Digital Discount Mobile App
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 200 | 65 | 13000 |  |  | 0 | 13000 |  | 13000
2. Planning | 600 | 60 | 36000 |  |  | 0 | 36000 |  | 36000
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Course design and development |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Supplier management training | 100 | 60 | 6000 | 50 | 150 | 7500 | 13500 | 5000 | 18500
3.1.2 Negotiating skills training | 20 | 55 | 1100 | 50 | 150 | 7500 | 8600 | 500 | 9100
3.1.3 Project management training | 400 | 60 | 24000 | 50 | 150 | 7500 | 31500 | 500 | 32000
3.1.4 Software applications training | 40 | 60 | 2400 | 10 | 150 | 1500 | 3900 | 1000 | 4900
3.2 Course administration | 40 | 55 | 2200 | 30 | 250 | 7500 | 9700 | 8000 | 17700
3.3.Course evaluation | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
3.4 Stakeholder communications | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
4. Monitoring and Controlling | 500 | 55 | 27500 |  |  | 0 | 27500 |  | 27500
5. Closing | 200 | 55 | 11000 |  |  | 0 | 11000 |  | 11000
Subtotal | [8 empty] | 202700
Reserves |  |  | 0 |  |  | 0 | 0 |  | 20270
Total | 2700 |  | 156200 | 190 | 850 | 31500 | 187700 | 15000 | 222970
Assumptions List:
Prior knowledge has been collected
Market rates may be vary
Rates are taken according to current situation

## Effort Value Estimate
Tasks | Effort | Impact
1. Initiating | High | High | Requirememts gathering |  | Coding and Design
2. Planning | Low | Low
3. Executing | Low | High | ✗ | Gather requirements | ✓ | Digital app portal
3.1 Course design and development | High | Low | ✓ | Validate requirements | ✗ | User interface
3.1.1 Supplier management training | High | High | ✗ | Requirements specification | ✗ | Backend design
3.1.2 Negotiating skills training | Low | High |  |  |  | Database design
3.1.3 Project management training | High | Low
3.1.4 Software applications training | Low | Low
3.2 Course administration | Low | Low
3.3.Course evaluation | High | Low
3.4 Stakeholder communications | High | High
4. Monitoring and Controlling | Low | High
|  |  | project risk plan |  | Project management plan
|  |  | ✗ | Risk register | ✓ | Project scope plan
|  |  | ✓ | Project probability plan | ✗ | Work breakdown structure
|  |  | ✓ | Cost estimate plan | ✓ | Earned value plan
EFFORT
HIGH
LOW
IMPACT
HIGH
LOW